## Table 1
Transmission Owner | Terminal 1 | Terminal 2 | Line Length in Miles | In-Service | In-Service Date Prior to Year | Operating Nominal Voltage (kV) | Design Nominal Voltage (kV) | Number of circuits | Summer Thermal Ratings | Winter Thermal Ratings | Project Description / Conductor Size | Category
NYPA | Niagara | Rochester | -70.2 | W | 2020 | 345 | 345 | 1 | 2177 | 2662 | 2-795 ACSR | Line
NYPA | Somerset | Rochester | -44 | W | 2020 | 345 | 345 | 1 | 2177 | 2662 | 2-795 ACSR | Line
O & R/ConEd | Ladentown | Buchanan | -9.5 | S | 2021 | 345 | 345 | 1 | 3000 | 3211 | 2-2493 ACAR | Line
NYPA | Station 255 (New Station) | Rochester | 3.8 | W | 2020 | 345 | 345 | 2 | 2177 | 2662 | 2-795 ACSR | Line
RGE | Station 255 (New Station) | Rochester | 3.8 | W | 2020 | 345 | 345 | 1 | 2177 | 2662 | 2-795 ACSR | Line
O & R/ConEd | Lovett 345 kV Station (New) | Buchanan | 4 | S | 2021 | 345 | 345 | 1 | 3000 | 3211 | 2-2493 ACAR | Line
O & R/ConEd | Ladentown | Lovett 345 kV Station (New) | 5.5 | S | 2021 | 345 | 345 | 1 | 3000 | 3211 | 2-2493 ACAR | Line
NYPA | Somerset | Station 255 (New Station) | 40.2 | W | 2020 | 345 | 345 | 1 | 2177 | 2662 | 2-795 ACSR | Line
NYPA | Niagara | Station 255 (New Station) | 66.4 | W | 2020 | 345 | 345 | 1 | 2177 | 2662 | 2-795 ACSR | Line
NYPA | Moses | Adirondack | 78 | S | 2023 | 230 | 345 | 2 | 1088 | 1329 | Replace 78 miles of both Moses-Adirondack 1&2 | Line
LIPA | Pilgrim | West Bus | -11.86 | In-Service | 2019 | 138 | 138 | 1 | 2087 | 2565 | 2493 ACAR | Line
LIPA | Pilgrim | Kings | 4.81 | In-Service | 2019 | 138 | 138 | 1 | 2087 | 2565 | 2493 ACAR | Line
O & R | Burns | West Nyack | 5 | S | 2023 | 138 | 138 | 1 | 940 | 940 | UG Cable | Line
O & R | Burns | Corporate Drive | 5 | W | 2024 | 138 | 138 | 1 | 1980 | 2120 | 1272 ACSS | Line
O & R | Ramapo (NY) | South Mahwah | 5.5 | W | 2022 | 138 | 138 | 2 | 1980 | 2120 | 1272 ACSS | Line
LIPA | Valley Stream | East Garden City | 7.36 | S | 2021 | 138 | 138 | 1 | 1171 | 1171 | 2000 SQMM XLPE | Line
LIPA | West Bus | Kings | 8.25 | In-Service | 2019 | 138 | 138 | 1 | 2087 | 2565 | 2493 ACAR | Line
LIPA | Riverhead | Wildwood | 10.63 | S | 2021 | 138 | 138 | 1 | 1399 | 1709 | 1192ACSR | Line
LIPA | Syosset | Shore Rd | 11 | S | 2026 | 138 | 138 | 1 | 1171 | 1171 | 2000 SQMM XLPE | Line
LIPA | Riverhead | Canal | 16.49 | S | 2021 | 138 | 138 | 1 | 1000 | 1110 | 2368 KCMIL (1200 mm²) Copper XLPE | Line
O & R | Ramapo | Sugarloaf | 17 | W | 2024 | 138 | 138 | 1 | 1980 | 2120 | 1272 ACSS | Line
NGRID | Mohican | Luther Forest | -34.47 | In-Service | 2019 | 115 | 115 | 1 | 937 | 1141 | New Schaghticoke Switching Station | Line
NGRID | Spier | Luther Forest (#302) | -34.21 | S | 2020 | 115 | 115 | 1 | 916 | 1070 | New Lasher Rd Switching Station | Line
NGRID | Spier | Rotterdam (#2) | -32.74 | S | 2020 | 115 | 115 | 1 | 1168 | 1416 | New Lasher Rd Switching Station | Line
NGRID | Schodack | Churchtown | -26.74 | In-Service | 2019 | 115 | 115 | 1 | 937 | 1141 | Line removal tapped by Falls Park Project | Line
NGRID | Battenkill | Eastover Road | -22.72 | In-Service | 2019 | 115 | 115 | 1 | 937 | 1141 | New Schaghticoke Switching Station | Line
NGRID | Mountain | Lockport | 0.08 | S | 2021 | 115 | 115 | 2 | 174MVA | 199MVA | Mountain-Lockport 103/104 Bypass | Line
NGRID | Cortland | Clarks Corners | 0.2 | S | 2023 | 115 | 115 | 1 | 147MVA | 170MVA | Replace 0.2 miles of 1(716) line and series equipment | Line
RGE | Mortimer | Station 251 (Upgrade Line) | 1 | W | 2024 | 115 | 115 | 1 | 400MVA | 400MVA | Line Upgrade | Line
NYSEG | Wood Street | Carmel | 1.34 | In-Service | 2019 | 115 | 115 | 1 | 261 MVA | 261 MVA | 477 ACSR | Line
RGE | Station 262 | Station 23 | 1.46 | W | 2020 | 115 | 115 | 1 | 2008 | 2008 | Underground Cable | Line
CHGE | Fishkill Plains | East Fishkill | 2.05 | S | 2020 | 115 | 115 | 1 | 995 | 1218 | 1-1033.5 ACSR | Line
NGRID | Inghams | Saint Johnsville | 2.94 | W | 2024 | 115 | 115 | 1 | 1114 | 1359 | Reconductor 2.94mi of 2/0 + 4/0 Cu (of 7.11mi total) to 795 ACSR | Line
RGE | Station 33 | Station 262 | 2.97 | W | 2020 | 115 | 115 | 1 | 2008 | 2008 | Underground Cable | Line
NGRID | Maplewood | Menands | 3 | S | 2023 | 115 | 115 | 1 | 220 MVA | 239 MVA | Reconductor approx 3 miles of 115kV Maplewood – Menands #19 | Line
NGRID | Maplewood | Reynolds | 3 | S | 2023 | 115 | 115 | 1 | 217 MVA | 265 MVA | Reconductor approx 3 miles of 115kV Maplewood – Reynolds Road #31 | Line
NGRID | Niagara | Packard | 3.4 | W | 2021 | 115 | 115 | 1 | 344MVA | 449MVA | Replace 3.4 miles of 192 line | Line
NGRID | Mohican | Butler | 3.5 | S | 2019 | 115 | 115 | 1 | TBD | TBD | Replace 3.5 miles of conductor w/min 336.4 ACSR | Line
NGRID | Niagara | Packard | 3.7 | S | 2022 | 115 | 115 | 1 | 344MVA | 449MVA | Replace 3.7 miles of 191 line | Line
NGRID | Niagara | Packard | 3.7 | W | 2022 | 115 | 115 | 2 | 344MVA | 449MVA | Replace 3.7 miles of 193 and 194 lines | Line
CHGE | Modena | Galeville | 4.62 | W | 2022 | 115 | 115 | 1 | 1010 | 1245 | 1-795 ACSR | Line
NGRID/NYSEG | Erie St | Gardenville | 5.5 | S | 2026 | 115 | 115 | 1 | 139MVA | 179MVA | Packard-Erie / Niagara-Garenville Reconfiguration, Gardenville add breakers | Line
CHGE | St. Pool | High Falls | 5.61 | W | 2022 | 115 | 115 | 1 | 1010 | 1245 | 1-795 ACSR | Line
NGRID | Albany Steam | Greenbush | 6.14 | In-Service | 2019 | 115 | 115 | 2 | 1190 | 1527 | Reconductor Albany - Greenbush 115kV lines 1 & 2 | Line
NGRID | Gardenville | Big Tree | 6.3 | W | 2022 | 115 | 115 | 1 | 221MVA | 221MVA | Gardenville-Arcade #151 Loop-in-and-out of NYSEG Big Tree | Line
NGRID | Luther Forest | Schaghticoke (New Station) | 6.34 | In-Service | 2019 | 115 | 115 | 1 | 1280 | 1563 | New Schaghticoke Switching Station | Line
NGRID | Huntley | Lockport | 6.9 | S | 2020 | 115 | 115 | 2 | 1303 | 1380 | Replace 6.9 miles of 36 and 37 lines | Line
NGRID | Rotterdam | Curry Rd | 7 | S | 2020 | 115 | 115 | 1 | 808 | 856 | Replace 7.0 miles of mainly 4/0 Cu conductor with 795kcmil ACSR 26/7 | Line
NGRID | Rotterdam | Woodlawn | 7 | S | 2020 | 115 | 115 | 1 |  |  | Replace 7.0 miles of mainly 4/0 Cu conductor with 795kcmil ACSR 26/7 | Line
NGRID | GE | Geres Lock | 7.14 | S | 2020 | 115 | 115 | 1 | 785 | 955 | Reconductoring 4/0CU & 336 ACSR to 477 ACCR (Line #8) | Line
RGE | Station 418 | Station 48 | 7.6 | W | 2024 | 115 | 115 | 1 | 175 MVA | 225 MVA | New 115kV Line | Line
NYSEG | Coddington | E. Ithaca (to Coddington) | 8.07 | W | 2020 | 115 | 115 | 1 | 307 MVA | 307 MVA | 665 ACCR | Line
NGRID | Schaghticoke (New Station) | Eastover Road | 8.41 | In-Service | 2019 | 115 | 115 | 1 | 937 | 1141 | New Schaghticoke Switching Station | Line
CHGE | Galeville | Kerhonkson | 8.96 | W | 2022 | 115 | 115 | 1 | 1010 | 1245 | 1-795 ACSR | Line
NGRID | Packard | Huntley | 9.1 | W | 2023 | 115 | 115 | 1 | 262MVA | 275MVA | Walck-Huntley #133, Packard-Huntley #130 Reconductor | Line
NGRID | Walck | Huntley | 9.1 | W | 2023 | 115 | 115 | 1 | 262MVA | 275MVA | Walck-Huntley #133, Packard-Huntley #130 Reconductor | Line
NGRID | Falls Park | Churchtown | 9.41 | In-Service | 2019 | 115 | 115 | 1 | 175 MVA | 206 MVA | Loop for NYSEG Sub Will Reconfigure NG Line #14 Into Two New Lines | Line
RGE | Station 255 (New Station) | Station 418 | 9.6 | W | 2020 | 115 | 115 | 1 | 1506 | 1807 | New 115kV Line | Line
NGRID | Stoner | Rotterdam | 9.81 | W | 2025 | 115 | 115 | 1 | 1398 | 1708 | Reconductor 9.81mi of 4/0 Cu + 336.4 ACSR (of 23.12mi total) to 1192.5 ACSR | Line
NGRID | Meco | Rotterdam | 9.81 | W | 2025 | 115 | 115 | 1 | 1398 | 1708 | Reconductor 9.96mi of 4/0 Cu + 336.4 ACSR (of 30.79mi total) to 1192.5 ACSR | Line
CHGE | High Falls | Kerhonkson | 10.03 | W | 2022 | 115 | 115 | 1 | 1010 | 1245 | 1-795 ACSR | Line
NGRID | Clay | Dewitt | 10.24 | S | 2021 | 115 | 115 | 1 | 220MVA | 268MVA | Reconductor 4/0 CU to 795ACSR | Line
CHGE | Sugarloaf | NY/NJ State Line | 10.3 | W | 2022 | 115 | 115 | 2 | N/A | N/A | Retire SD/SJ Lines | Line
NGRID | Lasher Rd (New Station) | Rotterdam | 11.05 | S | 2020 | 115 | 115 | 1 | 2080 | 2392 | New Lasher Rd Switching Station | Line
RGE | Station 255 (New Station) | Station 23 | 11.1 | W | 2020 | 115 | 115 | 1 | 1506 | 1807 | New 115kV Line | Line
CHGE | Rock Tavern | Sugarloaf | 12.1 | W | 2022 | 115 | 115 | 1 | N/A | N/A | Retire SL Line | Line
NGRID | Lasher Rd (New Station) | Luther Forest | 12.49 | S | 2020 | 115 | 115 | 1 | 990 | 1070 | New Lasher Rd Switching Station | Line
NGRID | Clay | Teall | 12.75 | S | 2021 | 115 | 115 | 1 | 220 MVA | 268MVA | Reconductor 4/0 CU to 795ACSR | Line
NGRID | Battenkill | Schaghticoke (New Station) | 14.31 | In-Service | 2019 | 115 | 115 | 1 | 937 | 1141 | New Schaghticoke Switching Station | Line
NGRID | Mortimer | Pannell | 15.7 | S | 2026 | 115 | 115 | 2 | 221MVA | 270MVA |  | Line
NGRID | Falls Park | Schodack(NG) | 17.33 | In-Service | 2019 | 115 | 115 | 1 | 186 MVA | 227 MVA | Loop for NYSEG Sub Will Reconfigure NG Line #14 Into Two New Lines | Line
NGRID | Gardenville | Dunkirk | 20.5 | S | 2024 | 115 | 115 | 2 | 1105 | 1346 | Replace 20.5 miles of 141 and 142 lines | Line
NGRID | Spier | Lasher Rd (New Station) | 21.69 | S | 2020 | 115 | 115 | 1 | 1168 | 1416 | New Lasher Rd Switching Station | Line
NGRID | Spier | Lasher Rd (New Station) | 21.72 | S | 2020 | 115 | 115 | 1 | 916 | 1118 | New Lasher Rd Switching Station | Line
NGRID | Niagara | Gardenville | 26.3 | S | 2026 | 115 | 115 | 1 | 275MVA | 350MVA | Packard-Erie / Niagara-Garenville Reconfiguration | Line
RGE | Station 168 | Mortimer (NG Trunk #2) | 26.4 | W | 2022 | 115 | 115 | 1 | 145 MVA | 176 MVA | Station 168 Reinforcement Project | Line
NGRID | Mohican | Schaghticoke (New Station) | 28.13 | In-Service | 2019 | 115 | 115 | 1 | 937 | 1141 | New Schaghticoke Switching Station | Line
NGRID | Packard | Gardenville | 28.2 | S | 2026 | 115 | 115 | 2 | 168MVA | 211 MVA | Packard-Gardenville Reactors, Packard-Erie / Niagara-Garenville Reconfiguration | Line
NGRID | Big Tree | Arcade | 28.6 | W | 2022 | 115 | 115 | 1 | 129MVA | 156MVA | Gardenville-Arcade #151 Loop-in-and-out of NYSEG Big Tree | Line
RGE | Station 168 | Elbridge (NG Trunk # 6) | 45.5 | W | 2022 | 115 | 115 | 1 | 145 MVA | 176 MVA | Station 168 Reinforcement Project | Line
NGRID | Lockport | Mortimer | 56.5 | S | 2022 | 115 | 115 | 3 | - | - | Replace Cables Lockport-Mortimer #111, 113, 114 | Line
LIPA | Meadowbrook | East Garden City | -3.11 | S | 2020 | 69 | 69 | 1 | 458 | 601 | 4/0 CU | Line
LIPA | West Hempstead | East Garden City | -2.92 | In-Service | 2019 | 69 | 69 | 1 | 1158 | 1245 | 477 ACSS | Line
NGRID | Schenectady International | Rotterdam | 0.93 | W | 2024 | 69 | 115 | 1 | 1114 | 1359 | Reconductor 0.93mi of 4/0 Cu + 336.4 ACSR (of 21.08mi total) to 795 ACSR | Line
NGRID | Rotterdam | Schoharie | 0.93 | W | 2024 | 69 | 115 | 1 | 1114 | 1359 | Reconductor 0.93mi of 4/0 Cu (of 21.08mi total) to 795 ACSR | Line
LIPA | West Hempstead | Hempstead | 0.97 | In-Service | 2019 | 69 | 69 | 1 | 1158 | 1245 | 477 ACSS | Line
LIPA | Hempstead | East Garden City | 1.95 | In-Service | 2019 | 69 | 69 | 1 | 1158 | 1245 | 477 ACSS | Line
O & R | Deerpak | Port Jervis | 2 | S | 2021 | 69 | 69 | 1 |  | 1604 |  | Line
O & R | Shoemaker | Pocatello | 2 | W | 2023 | 69 | 69 | 1 | 1604 | 1723 | 795 ACSS | Line
LIPA | Lindbergh | Meadowbrook | 2.11 | S | 2020 | 69 | 69 | 1 | 458 | 601 | 4/0 CU | Line
LIPA | East Garden City | Lindbergh | 2.5 | S | 2020 | 69 | 69 | 1 | 575 | 601 | 750 kcmil CU | Line
O & R | Harings Corner (RECO) | Closter (RECO) | 3.2 | S | 2020 | 69 | 69 | 1 | 1098 | 1312 | UG Cable | Line
LIPA | Southampton | Deerfield | 4 | S | 2025 | 69 | 138 | 1 | 1171 | 1171 | 2000 SQMM XLPE | Line
LIPA | Canal | Southampton | 5.2 | In-Service | 2019 | 69 | 69 | 1 | 1107 | 1169 | 2500 kcmil XLPE CU | Line
O & R | Westtown | Port Jervis | 7 | S | 2021 | 69 | 69 | 1 |  | 1604 |  | Line
O & R | West Nyack (NY) | Harings Corner (RECO) | 7 | W | 2026 | 69 | 138 | 1 | 1604 | 1723 | 795 ACSS | Line
CHGE | Hurley Ave | Saugerties | 11.4 | W | 2022 | 69 | 115 | 1 | 1114 | 1359 | 1-795 ACSR | Line
O & R | Sugarloaf | Shoemaker | 12 | W | 2023 | 69 | 138 | 2 | 1062 | 1141 | 397 ACSS | Line
CHGE | Saugerties | North Catskill | 12.46 | W | 2023 | 69 | 115 | 1 | 1114 | 1359 | 1-795 ACSR | Line
LIPA | Elmont | Floral Park | -1.59 | S | 2020 | 34.5 | 34.5 | 1 | 644 | 816 | 477 AL | Line
LIPA | Elmont | Belmont | 1.82 | S | 2020 | 34.5 | 34.5 | 1 | 342 | 457 | 2/0 CU | Line
LIPA | Belmont | Floral Park | 2.04 | S | 2020 | 34.5 | 34.5 | 1 | 644 | 816 | 477 AL | Line
LIPA | Amagansett | Montauk | -13 | S | 2021 | 23 | 23 | 1 | 577 | 657 | 750 kcmil CU | Line
LIPA | Navy Road | Montauk | 0.26 | S | 2021 | 23 | 23 | 1 | 577 | 657 | 750 kcmil CU | Line
LIPA | Amagansett | Navy Road | 12.74 | S | 2021 | 23 | 23 | 1 | 577 | 657 | 750 kcmil CU | Line
LIPA | Deer Park | Deer Park | - | W | 2019 | 69 | 69 | 1 | N/A | N/A | Install 27 MVAR Cap Bank | Capacitor Bank
LIPA | MacArthur | MacArthur | - | W | 2019 | 69 | 69 | 1 | N/A | N/A | Install 27 MVAR Cap Bank | Capacitor Bank
NGRID | Seneca | Seneca | - | In-Service | 2019 | 115/22 | 115/22 | - | 50MVA | 50MVA | Damage/Failure on TR2 | Damage
NGRID | Rosa Rd | Rosa Rd | - | S | 2020 | 115 | 115 |  | N/A | N/A | Install 35.2MVAR Cap Bank at Rosa Rd | Capacitor Bank
NGRID | Rotterdam | Rotterdam | - | S | 2020 | 115 | 115 | 2 | N/A | N/A | Install Series Reactors at Rotterdam Station on lines 17 & 19 | Series Reactor
NGRID | Gardenville 115kV | Gardenville 115kV | - | S | 2020 | - | - | - | - | - | Rebuild of Gardenville 115kV Station to full breaker and a half | Station
NGRID | Oswego | Oswego | - | W | 2020 | 115 | 115 |  | N/A | N/A | Rebuild of Oswego 115kV Station | Station
NGRID | Huntley 115kV | Huntley 115kV | - | S | 2021 | 230 | 230 | - | N/A | N/A | Rebuild of Huntley 115kV Station | Station
NGRID | Mortimer | Mortimer | - | S | 2021 | 115 | 115 |  | N/A | N/A | Second 115kV Bus Tie Breaker at Mortimer Station | Breaker
NGRID | New Bethlehem | New Bethlehem | - | S | 2021 | 115 | 115 |  | N/A | N/A | New Bethlehem 115/13.2kV station | Station
NGRID | Royal Ave | Royal Ave | - | S | 2021 | 115/13.2 | 115/13.2 | - | - | - | Install new 115-13.2 kV distribution substation in Niagara Falls (Royal Ave) | Station
NGRID | South Oswego | Indeck (#6) | - | S | 2022 | 115 | 115 | 1 | - | - | Install High Speed Clearing on Line #6 | Reconfiguration
NGRID | Porter | Porter | - | S | 2022 | 230 | 230 |  | N/A | N/A | Porter 230kV upgrades | Reconfiguration
NGRID | Coffeen | Coffeen | - | S | 2022 | 115 | 115 | - | TBD | TBD | Terminal equipment replacements | Reconfiguration
NGRID | Browns Falls | Browns Falls | - | S | 2022 | 115 | 115 | - | TBD | TBD | Terminal equipment replacements | Reconfiguration
NGRID | Taylorville | Taylorville | - | S | 2022 | 115 | 115 | - | TBD | TBD | Terminal equipment replacements | Reconfiguration
NGRID | Elm St | Elm St | - | S | 2023 | 230/23 | 230/23 | - | 118MVA | 133MVA | Replace TR2 as failure | Reconfiguration
NGRID | Kensington Terminal | Kensington Terminal | - | W | 2023 | 115/23 | 115/23 | - | 50MVA | 50MVA | Replace TR4 and TR5 | Reconfiguration
NGRID | Malone | Malone | - | S | 2023 | 115 | 115 | - | TBD | TBD | Station Rebuild | Reconfiguration
NGRID | Taylorville | Boonville | - | S | 2023 | 115 | 115 | - | TBD | TBD | Install series reactors on the 5 and 6 lines. Size TBD | Series Reactor
NGRID | Dunkirk | Laona | - | S | 2024 | 115 | 115 | 2 | N/A | N/A | Remove series reactors from New Road Switch Station and install new to Moons Switch Station | Removal
NGRID | Laona | Moons | - | S | 2024 | 115 | 115 | 2 | N/A | N/A | Remove series reactors from New Road Switch Station and install new to Moons Switch Station | Removal
NGRID | Dunkirk | Dunkirk | - | S | 2024 | 115 | 115 |  | N/A | N/A | Rebuild of Dunkirk 115kV Station | Reconfiguration
NGRID | Homer Hill | Homer Hill | - | S | 2024 | 115 | 115 | - | 116MVA | 141MVA | Homer Hill Replace five OCB | Reconfiguration
O & R | West Nyack | West Nyack | - | S | 2026 | 138 | 138 | 1 |  |  | Station Reconfiguration | Reconfiguration
NYPA | Astoria 138 kV | Astoria 13.8 kV | Astoria CC GSU Refurbishment | W | 2020 | 138 | 18 | 1 | 234 | 234 | Astoria CC GSU Refurbishment | Reconfiguration
NYPA | Niagara 230 kV | Niagara 115 kV | Autotransformer | S | 2020 | 230 | 115 | 1 | 240 MVA | 240 MVA | Replace Niagara AT #1 | Transformer
LIPA | Elwood | Elwood | Breaker | In-Service | 2019 | 138 | 138 |  | N/A | N/A | Install double bus tie - Operate Normally Open | Breaker
NYPA | Niagara 230 kV | Niagara 230 kV | Breaker | W | 2020 | 230 | 230 | 1 | N/A | N/A | Add a new breaker | Breaker
NGRID | Inghams 115kV | Inghams 115kV | Breaker | W | 2024 | 115 | 115 | - | 2000 | 2000 | Add series breaker to Inghams R15 (Inghams - Meco #15 115kV) | Breaker
NGRID | Golah | Golah | Cap Bank | In-Service | 2019 | 115 | 115 | 1 | 18MVAR | 18MVAR | Capacitor Bank | Capacitor Bank
NGRID | Batavia | Batavia | Cap Bank | In-Service | 2019 | 115 | 115 | 1 | 30MVAR | 30MVAR | Second Capacitor Bank | Capacitor Bank
LIPA | MacArthur | - | Cap Bank | S | 2020 | 69 | 69 | 1 | 27MVAR | 27 MVAR | Capacitor bank | Capacitor Bank
O & R | West Nyack | West Nyack | Cap Bank | S | 2020 | 138 | 138 | 1 | - | - | Capacitor Bank | Capacitor Bank
LIPA | Deer Park | - | Cap Bank | S | 2021 | 69 | 69 | 1 | 27MVAR | 27 MVAR | Capacitor bank | Capacitor Bank
O & R | Little Tor | - | Cap Bank | S | 2021 | 138 | 138 | 1 | 32 MVAR | 32 MVAR | Capacitor bank | Capacitor Bank
O & R | Montvale (RECO) | - | Cap Bank | S | 2024 | 69 | 69 | 1 | 32 MVAR | 32 MVAR | Capacitor bank | Capacitor Bank
RGE | Station 42 | Station 23 | Phase Shifter | In-Service | 2019 | 115 | 115 | 1 | 253 MVA | 253 MVA | Phase Shifter | Phase Shifter
LIPA | Syosset | Shore Rd | Phase Shifter | S | 2026 | 138 | 138 | 1 | TBD | TBD | Phase Shifter | Phase Shifter
NYSEG | Fraser 115 | Fraser 115 | Rebuild | W | 2022 | 115 | 115 |  | N/A | N/A | Station Rebuild to 4 bay BAAH | Station
NYSEG | Erie Street Rebuild | Erie Street Rebuild | Rebuild | W | 2022 | 115 | 115 |  |  |  | Station Rebuild | Station
NYSEG | Big Tree Road | Big Tree Road | Rebuild | W | 2022 | 115 | 115 |  |  |  | Station Rebuild | Station
ConEd | Jamaica | Jamaica | Reconfiguration | In-Service | 2019 | 138 | 138 |  | N/A | N/A | Reconfiguration | Reconfiguration
ConEd | East 13th Street | East 13th Street | Reconfiguration | In-Service | 2019 | 345 | 345 |  | N/A | N/A | Reconfiguration (xfmr 10 -xfmr 11) | Reconfiguration
LIPA | Far Rockaway | Far Rockaway | Reconfiguration | In-Service | 2019 | 34.5 | 34.5 |  | N/A | N/A | Reconfigure 34.5 kV switchgear | Reconfiguration
NGRID | Mortimer | Mortimer | Reconfiguration | In-Service | 2019 | 115 | 115 | 1 | N/A | N/A | Reconfiguration of Station | Reconfiguration
ConEd | Buchanan North | Buchanan North | Reconfiguration | S | 2020 | 345 | 345 |  | N/A | N/A | Reconfiguration (bus work related to decommissioning of Indain Point 2) | Reconfiguration
ConEd | Farragut | Farragut | Reconfiguration | S | 2024 | 138 | 138 |  | N/A | N/A | Install PASS Breaker | Reconfiguration
NGRID | Golah | Golah | Reconfiguration | S | 2024 | 115 | 115 |  | - | - | Add a Golah 115kV bus tie breaker | Reconfiguration
NYSEG | Delhi | Delhi | Removal | W | 2022 | 115 | 115 |  | N/A | N/A | Remove 115 substation and terminate existing lines to Fraser 115 (short distance) | Removal
NYSEG | Westover 115 | Westover | Removal | W | 2024 | 115 | 115 |  | N/A | N/A | Remove 115 substation and terminate existing lines to Oakdale 115 (short distance) | Removal
NYPA | Moses 230 kV | Adirondack 230 kV | Series Compensation | S | 2021 | 230 | 230 | - | ±13.2kV | ±13.2kV | Voltage Source Series Compensation | Series Compensation
NYPA | Astoria Annex | Astoria Annex | Shunt Reactor | W | 2021 | 345 | 345 | 2 | TBD | TBD |  | Shunt Reactor
NYPA | Fraser Annex | Fraser Annex | SSR Detection | S | 2020 | 345 | 345 | 1 | 1793 MVA | 1793 MVA | MSSC SSR Detection Project | SSR Detection
CHGE | Hurley Avenue | Leeds | Static synchronous | S | 2021 | 345 | 345 | 1 | 2336 | 2866 | 21% Compensation | Static Synchronous
ConEd | East 13th Street | East 13th Street | xfmr | In-Service | 2019 | 345 | 345 |  | N/A | N/A | Replacing xfmr 10 and xfmr 11 | Transformer
ConEd | Gowanus | Gowanus | xfmr | In-Service | 2019 | 345 | 345 |  | N/A | N/A | Replacing xfmr T2 | Transformer
NYSEG | Flat Street | Flat Street | xfmr | In-Service | 2019 | 115/34.5 | 115/34.5 | 2 | 40MVA | 45.2MVA | Transformer #2 | Transformer
NYSEG | Falls Park | Falls Park | xfmr | In-Service | 2019 | 115/34.5 | 115/34.5 | 1 | 62 MVA | 70 MVA | Transformer #1 | Transformer
RGE | Station 23 | Station 23 | xfmr | In-Service | 2019 | 115/11.5/1 1.5 | 115/11.5/ 11.5 | 2 | 75 MVA | 84 MVA | Transformer | Transformer
RGE | Station 23 | Station 23 | xfmr | W | 2019 | 115/34.5 | 115/34.5 | 2 | 75 MVA | 84 MVA | Transformer | Transformer
CHGE | North Chelsea | North Chelsea | xfmr | S | 2020 | 115/69 | 115/69 | 1 | 564 | 728 | Replace Transformer 1 | Transformer
CHGE | North Catskill | North Catskill | xfmr | W | 2020 | 115/69 | 115/69 | 2 | 560 | 726 | Replace Transformer 4 & 5 | Transformer
NGRID | Elm St | Elm St | xfmr | S | 2020 | 230/23 | 230/23 | 1 | 118MVA | 133MVA | Add a fourth 230/23kV transformer | Transformer
NGRID | Gardenville 230kV | Gardenville 115kV | xfmr | S | 2020 | 230/115 | 230/115 | - | 347 MVA | 422 MVA | Replacement of 230/115kV TB#4 stepdown with larger unit | Transformer
NYSEG | Watercure Road | Watercure Road | xfmr | W | 2020 | 345/230 | 345/230 | 1 | 426 MVA | 494 MVA | Transformer #2 and Station Reconfiguration | Transformer
NYSEG | Willet | Willet | xfmr | W | 2020 | 115/34.5 | 115/34.5 | 1 | 39 MVA | 44 MVA | Transformer #2 | Transformer
O & R | Ramapo | Ramapo | xfmr | S | 2020 | 345/138 | 345/138 | 1 | 731 | 731 | - | Transformer
RGE | Station 262 | Station 262 | xfmr | W | 2020 | 115/34.5 | 115/34.5 | 1 | 58.8MVA | 58.8MVA | Transformer | Transformer
RGE | Station 255 (New Station) | Station 255 (New Station) | xfmr | W | 2020 | 345/115 | 345/115 | 1 | 400 MVA | 450 MVA | Transformer | Transformer
RGE | Station 255 (New Station) | Station 255 (New Station) | xfmr | W | 2020 | 345/115 | 345/115 | 2 | 400 MVA | 450 MVA | Transformer | Transformer
NGRID | Gardenville 230kV | Gardenville 115kV | xfmr | S | 2021 | 230/115 | 230/115 | - | 347 MVA | 422 MVA | Replacement of 230/115kV TB#3 stepdown with larger unit | Transformer
NGRID | Mortimer | Mortimer | xfmr | S | 2021 | 115 | 115 |  | 50MVA | 50MVA | Replace Mortimer 115/69kV Transformer | Transformer
NYPA | St. Lawrence 230kV | St. Lawrence 115kV | xfmr | S | 2021 | 230/115 | 230/115 | 1 | TBD | TBD | Replacement of St. Lawrence AutoTransformer #2 | Transformer
NYPA | Plattsburg 230 kV | Plattsburg 115 kV | xfmr | W | 2021 | 230/115 | 230/115 | 1 | 249 | 288 | Refurbishment of Plattsburgh Auto Transformer #1 | Transformer
O & R | Lovett 345 kV Station (New) | Lovett | xfmr | S | 2021 | 345/138 | 345/138 | 1 | 562 MVA | 562 MVA | Transformer | Transformer
CHGE | Kerhonkson | Kerhonkson | xfmr | W | 2022 | 115/69 | 115/69 | 1 | 564 | 728 | Add Transformer 3 | Transformer
CHGE | Kerhonkson | Kerhonkson | xfmr | W | 2022 | 115/69 | 115/69 | 1 | 564 | 728 | Add Transformer 4 | Transformer
NGRID | Golah | Golah | xfmr | S | 2022 | 69 | 69 |  | 50MVA | 50MVA | Replace Golah 69/34.5kV Transformer | Transformer
NYPA | Niagara 345 kV | Niagara 230 kV | xfmr | W | 2022 | 345/230 | 345/230 | 1 | TBD | TBD | Replacement of Niagara AutoTransformer #3 | Transformer
NYSEG | South Perry | South Perry | xfmr | W | 2022 | 115/34.5 | 115/34.5 | 1 | 59 MVA | 67 MVA | Transformer #3 | Transformer
NYSEG | South Perry | South Perry | xfmr | W | 2022 | 230/115 | 230/115 | 1 | 246 MVA | 291 MVA | Transformer | Transformer
NYSEG | Fraser | Fraser | xfmr | W | 2022 | 345/115 | 345/115 | 1 | 305 MVA | 364 MVA | Transformer #2 and Station Reconfiguration | Transformer
NYSEG | Meyer | Meyer | xfmr | W | 2022 | 115/34.5 | 115/34.5 | 2 | 59.2MVA | 66.9MVA | Transformer #2 | Transformer
RGE | Station 127 | Station 127 | xfmr | W | 2022 | 115/34.5 | 115/34.5 | 1 | 75MVA | 75MVA | Transformer #2 | Transformer
NYPA | Niagara 345 kV | Niagara 230 kV | xfmr | W | 2023 | 345/230 | 345/230 | 1 | TBD | TBD | Replacement of Niagara AutoTransformer #5 | Transformer
NYSEG | Gardenville | Gardenville | xfmr | W | 2023 | 230/115 | 230/115 | 1 | 316 MVA | 370 MVA | NYSEG Transformer #3 and Station Reconfiguration | Transformer
NYSEG | Wood Street | Wood Street | xfmr | W | 2023 | 345/115 | 345/115 | 1 | 327 MVA | 378 MVA | Transformer #3 | Transformer
ConEd | Rainey | Corona | xfmr/Phase shifter | In-Service | 2019 | 345/138 | 345/138 | 1 | 268 MVA | 320 MVA | xfmr/Phase shifter | Transformer
ConEd | Hudson Ave East | New Vinegar Hill | xfmrs/PARs/Feeders | S | 2024 | 138/27 | 138/27 |  | N/A | N/A | New Hudson Ave Distribution Switching Station | Transformer
NGRID | Ohio St | Ohio St |  | In-Service | 2019 | 115 | 115 |  | N/A | N/A | New Distribution Station at Ohio Street | Station
NGRID | Sodeman Rd | Sodeman Rd |  | In-Service | 2019 | 115 | 115 |  | N/A | N/A | New Distribution Station at Sodeman Road | Station
NGRID | Dewitt | Dewitt |  | In-Service | 2019 | 115 | 115 |  | N/A | N/A | New Distribution Station at Dewitt | Station
NYSEG | Falls Park 115/34.5kV |  |  | In-Service | 2019 | 115/34.5 | 115/34.5 |  |  |  | Tap to interconnect NG Line #14 | Tap to NG Line
NGRID | West Ashville | West Ashville |  | S | 2020 | 115 | 115 |  | N/A | N/A | New Distribution Station at West Ashville | Station
NGRID | Two Mile Creek | Two Mile Creek |  | S | 2020 | 115 | 115 |  | N/A | N/A | New Distribution Station at Two Mile Creek | Station
NGRID | Maple Ave | Maple Ave |  | S | 2020 | 115 | 115 |  | N/A | N/A | New Distribution Station at Maple Ave | Station
NGRID | Randall Rd | Randall Rd |  | S | 2020 | 115 | 115 |  | N/A | N/A | New Distribution Station at Randall Road | Station
RGE | Station 122-Pannell-PC1 | Station 122-Pannell-PC1 |  | S | 2020 | 345 | 345 | 1 | 1314 MVA-LTE | 1314 MVA-LTE | Relay Replacement | Station
NGRID | New Cicero | New Cicero |  | S | 2021 | 115 | 115 |  | N/A | N/A | New Distribution Station at New Cicero | Station
NGRID | Watertown | Watertown |  | S | 2022 | 115 | 115 |  | N/A | N/A | New Distribution Station at Watertown | Station
RGE | Station 82 | Station 251 (Upgrade Line) |  | W | 2024 | 115 | 115 | 1 | 400MVA | 400MVA | Line Upgrade | Reconfiguration